IMPLEMENTATION PLAN

Addressing Community Health Needs



**Roundup, Montana**

**2024-2027**

Table of Contents

[The Implementation Planning Process 3](#_Toc100914387)

[Prioritizing the Community Health Needs 5](#_Toc100914388)

[*Roundup Memorial Healthcare’s Existing Presence in the Community* 5](#_Toc100914389)

[*List of Available Community Partnerships and Facility Resources to Address Needs* 6](#_Toc100914390)

[*Musselshell County Indicators* 7](#_Toc100914391)

[*Public Health and Underserved Populations Consultation Summaries* 8](#_Toc100914392)

[Needs Identified and Prioritized 10](#_Toc100914393)

[*Prioritized Needs to Address* 10](#_Toc100914394)

[*Needs Unable to Address* 11](#_Toc100914395)

[Executive Summary 12](#_Toc100914396)

[Implementation Plan Grid 14](#_Toc100914397)

[Needs Not Addressed and Justification 25](#_Toc100914398)

[Dissemination of Needs Assessment 26](#_Toc100914399)

# The Implementation Planning Process

The implementation planning committee – comprised of Roundup Memorial Healthcare’s (RMH) leadership team– participated in an implementation planning process to systematically and thoughtfully respond to all issues and opportunities identified through their community health needs assessment (CHNA) process.

The Community Health Services Development (CHSD), community health needs assessment was performed in the spring of 2024 to determine the most important health needs and opportunities for Musselshell County, Montana. The CHSD project is administrated by the Montana Office of Rural Health (MORH) and funded in part through the Montana Health Research and Education Foundation (MHREF) Flex Grant. “Needs” were identified as the top issues or opportunities rated by respondents during the CHSD survey process or during focus groups (see page 10 for a list of “Needs Identified and Prioritized”). For more information regarding the needs identified, as well as the assessment process/approach/methodology, please refer to the facility’s assessment report, which is posted on the facility’s website (<https://www.rmhmt.org/documents/RMH_2024_CHNAReport_FinalRB-edits.pdf>).

The community steering and implementation planning committees identified the most important health needs to be addressed by reviewing the CHNA, secondary data, community demographics, and input from representatives of the broad interest of the community, including those with public health expertise (see page 8 for additional information regarding input received from community representatives).

The implementation planning committee reviewed the priority recommendations provided by the community steering committee and determined which needs or opportunities could be addressed considering RMH’s parameters of resources and limitations. The committee then prioritized the needs/opportunities using the additional parameters of the organizational vision, mission, and values, as well as existing and potential community partners. Participants then created a goal to achieve through strategies and activities, as well as the general approach to meeting the stated goal (i.e., staff member responsibilities, timeline, potential community partners, anticipated impact(s), and performance/evaluation measures).

The prioritized health needs as determined through the assessment process and which the facility will be addressing relates to the following healthcare issues:

* **Mental and behavioral health**
* **Awareness of health resources and services**
* **Access to specialty care**

In addressing the aforementioned issues, Roundup Memorial Healthcare seeks to:

1. Improve access to healthcare services
2. Enhance the health of the community
3. Advance medical or health knowledge

**Facility Mission:** To deliver safe, patient-centered care with the kindness we would want for ourselves and our family.

**Facility Vision**: To offer quality care and programs that meet community needs, exceed patients’ expectations, and are provided in a caring, convenient, cost-effective, and accessible manner.

**Implementation Planning Committee Members:**

* Terra Kellum – Executive Assistant and HR Generalist, RMH
* Amy Johnson – Practice Administrator, RMH
* Velma Bulcher – Director of Nursing Services, RMH
* Rachel Brewer – HR/Marketing Director, RMH
* Anne Marie Kloppel – Manager Regional Finance, RMH/Billings Clinic
* Valeri Russell – PA-C, Trauma Medical Director, Assistant Medical Director, RMH
* Rick Schroeder – Interim CEO, RMH

# Prioritizing the Community Health Needs

The steering and implementation planning committees completed the following to prioritize the community health needs:

1. Reviewed the facility’s presence in the community (i.e. activities already being done to address community need)
2. Considered organizations outside of the facility which may serve as collaborators in executing the facility’s implementation plan
3. Assessed the health indicators of the community through available secondary data
4. Evaluated the feedback received from consultations with those representing the community’s interests, including public health

## Roundup Memorial Healthcare’s Existing Presence in the Community

* Roundup Rodeo Sponsorship
* 4-H Sponsorship
* Baseball Team Sponsorship
* Flowers on Main Street Sponsorship
* Homes on the Range Health Education Talks
* Stop The Bleed
* Children’s helmet giveaways
* Sports physicals
* Local Emergency Preparedness Committee
* Markets on Main
* Backpack Program

## List of Available Community Partnerships and Facility Resources to Address Needs

* 3RNet
* Al-Anon
* Alcoholics Anonymous
* Area II Agency on Aging
* Centers for Medicaid and Medicare Services (CMS)
* Chiropractor (Bull Mountain Chiropractic- Dr. Brian Bushman )
* County Extension- Montana State University
* County Public Health
* County Sheriff’s Department
* Dentist (Jack Diagrepont, DDS)
* Fitness Center (A Healthy Life)
* Food bank
* General conditions management
* Golden Thimble (Provides clothing to community members in need)
* HRDC
* Massage Therapy
* Meals on Wheels
* Montana Department of Health and Human Services (MT DPHHS)
* Montana Office of Rural Health and Area Health Education Center
* Mountain-Pacific Quality Health
* Narcotics Anonymous
* Performance Improvement Network (PIN)
* Public Recreation and Parks (Riverwalk)
* Roundup Mental Health Center
* Saves INC. (To help victims of domestic violence and sexual assault)
* Senior Center
* Smoking cessation through CMHD
* St. Vincent’s Mobile mammography
* Veteran’s Affairs
* WIC
* Youth Cares

## Musselshell County Indicators

Population Demographics

* 94.1% of Musselshell County’s population identifies as white.
* 14.1% of Musselshell County’s population has disability status.
* 25.9% of Musselshell County’s population is 65 years and older.
* 13.6% of Musselshell County’s population has Veteran status.
* 8.5% of Musselshell County’s population has “No High School Diploma” as their highest degree attained; 42.8% are a “High school graduate (includes equivalency)”.

Size of County and Remoteness

* 4,766 people in Musselshell County.
* 2.5 people per square mile.

Socioeconomic Measures

* 17.3% of children live in poverty.
* 12.7% of persons are below the federal poverty level.
* 14% of adults (age<65) are uninsured; 8% of children (age<18) are uninsured.
* 10.0% of the population is enrolled in Medicaid.

Select Health Measures

* 28% of adults are considered obese.
* 28% of the adult population report physical inactivity.
* 18% of the adult population report smoking consistently.
* The rate of emergency department visits for intentional self-harm is 305.0 compared to 241.3 for Montana.
* 41.0% of adults living in frontier Montana report two or more chronic conditions.
* Montana’s veteran suicide rate (per 100,000 population) is 65.7 compared to 38.4 for the U.S.

Nearest Major Hospital

* Hospitals in Billings, MT are 50 miles from Roundup Memorial Healthcare.

## Public Health and Underserved Populations Consultation Summaries

Name/Organization March 7, 2024

Paula Snider – Homes on the Range

Terra Kellum – HR/Executive Assistant, Roundup Memorial Healthcare (RMH)

Dave Liggett – Community member

Cindy Moore – Retired Director of Nursing, community member

Rachel Brewer – HR/Marketing, RMH

Leann Fisk – CMHD

Megan Griffith – RN/Clinic lead, RMH

Kurt Lowartz – MD, RMH

Marcy Brookie – Area II on Aging

Natalie Goodwin – Community Heath Worker, RMH

Lucia Martinez – Social Services Point Coordinator, RMH

Velma Bulcher – Director of Nursing, RMH

Heather Welch – Business Office Manager, RMH

Stephanie Graben – Community member, Business owner (“Fat Straw”)

Amy Johnson – Practice Admin, RMH

Maria Owen – Acute Care Manager, RMH

Public and Community Health

* High prevalence of smoking during pregnancy
* Internet at home levels are disappointing
* Bad HPV vaccination numbers; not for lack of trying (not getting buy-in from schools, can’t even get foot in the door)
* Could do better in colorectal screening numbers (wouldn’t bank on given number for accuracy—clinic does a lot more cologards than cited; or at least people sign up for them a lot)

Population: Low-Income, Underinsured

* High underinsured children population—reflected in free lunch program
* High Medicaid enrollment

Population: Seniors

* High rates of arthritis—limits physical and thus mental health

Population: Youth

* Youth attempted suicide is very high, alarming
* Can be difficult to do health prevention/education in the schools
* High number of uninsured children

Population: Tribal/American Indian

* Large Veteran population
* Lots of disabled veterans

# Needs Identified and Prioritized

## *Prioritized Needs to Address*

1. The majority of respondents (50.8%) rated their community as “Somewhat healthy.”
2. Top health concerns for the community were “Alcohol/substance use” (59.4%), “Mental health issues (depression, anxiety, PTSD, etc.)” (36.7%), and “Overweight/obesity” (25.0%).
3. The second top component of a healthy community was “Access to healthcare services” (34.1%).
4. Most respondents had a “Good” (45.7%) or “Fair” (34.6%) knowledge of RMH services; the top methods of learning about available services were “Word of mouth/reputation” (61.7%), “Friends/family” (50.8%), “Healthcare provider” (32.8%), and “Social media/Facebook” (25.0%).
5. Access to healthcare would be improved with “More primary care providers (MD/DO)” (45.6%), “More information about available services” (36.8%), and “More Nurse Practitioners/Physician Assistants” (28.0%).
6. 50.0% of respondents felt lonely or isolated 1-2 days per month or more.
7. 58.7% of respondents experienced “Moderate” or “High” stress.
8. 19.0% of respondents rated their mental health as “Fair” and 3.2% rated theirs as “Poor.”
9. 46.0% of respondents indicated their lives have been impacted by substance use.
10. Key informants identified mental health and alcohol/drug use as top concerns in the community.
11. Key informants expressed the desire for more support groups in the community.
12. 93.0% of respondents have seen a primary care provider in the last three years, and 26.9% saw that provider at Billings Clinic.
13. Key informants identified the need for more communication about currently offered programs and services.
14. Key informants expressed the desire for more transportation options in Roundup.
15. Respondents expressed the desire for “Dermatology” services (34.3%) and “Orthopedic services” (17.6%).
16. 10.7% of respondents utilized a “Hearing check” as preventative service.
17. 33.3% of respondents said they delayed or deferred receiving care, and the top reasons were “Qualified provider not available” (34.1%) and “Too long to wait for appointment” (26.8%).

*Needs Unable to Address*

*(See page 25 for additional information)*

1. A top health concern was “Overweight/obesity” (25.0%), and the top three educational programs respondents expressed interest in were “Fitness” (39.8%), “Weight loss” (31.5%), and “Health and wellness” (30.6%). 31.8% of respondents got physical activity 3-5 times per month or less.
2. The third top component of a healthy community was “Affordable housing” (29.5%), and 54.8% of respondents did not think that there was adequate and affordable housing available in the community.

# Executive Summary

The following summary briefly represents the goals and corresponding strategies and activities which the facility will execute to address the prioritized health needs (from page 10). For more details regarding the approach and performance measures for each goal, please refer to the Implementation Plan Grid section, which begins on page 14.

**Goal 1: Improve access to mental and behavioral health resources in Musselshell County.**

**Strategy 1.1:** Enhance collaboration with local LCSW to increase awareness of and amount of services provided.

* Support LCSW to visit local meetings (e.g. community center, LEPC) to increase presence and visibility in the community.
* Work to determine LCSW’s role in organizing, facilitating, and maintaining local support groups.
* Determine feasibility of starting Grandparents Raising Grandchildren support group.
* Explore feasibility of cooperating with local churches to enable and sustain support groups for the community (e.g. grief support).

**Strategy 1.2:** Continue to support other mental and behavioral health resources in the community.

* + - Continue to coordinate with and support local school counselors and LCSWs.
		- Continue to explore ways to bolster in-patient mental health resources.

**Goal 2: Enhance community awareness of health resources and services offered through RMH.**

**Strategy 2.1:** Enhance marketing and publicity efforts to increase visibility of RMH in the community.

* + Inquire about putting hospital advertising materials in new kiosk downtown.
	+ Explore re-starting RMH presence on local radio station.
	+ Continue to engage with LEPC meetings and utilize this forum to advertise RMH services and resources.
	+ Continue to attend community events (e.g. Market on Main, Community Job Fair) to increase hospital presence in the community.

**Strategy 2.2**: Reinvigorate partnerships and relationships with various community entities.

* + Continue community education efforts.
	+ Define the role of the Hospital Foundation and its relationship with RMH.
	+ Continue to support and collaborate with the Hospital Foundation.
	+ Explore methods of increasing awareness of CHW presence and services through the clinic.
	+ Enhance clinical staff awareness of Patient Assistance program through increased communication.
	+ Monitor newly-introduced RMH Passenger Van to evaluate successes and room for improvement.

**Goal 3: Bolster access to specialty care services available through RMH.**

**Strategy 3.1:** Explore introduction of new specialty services offered through RMH.

* + - Explore re-introducing audiology and podiatry visiting specialists.
		- Explore feasibility of bringing visiting dermatology specialty services to RMH.
		- Determine if patient load is sufficient to warrant an ortho PA at RMH.

# Implementation Plan Grid

|  |
| --- |
| **Goal 1:** **Improve access to mental and behavioral health resources in Musselshell County.** |
| **Strategy 1.1:** Enhance collaboration with local LCSW to increase awareness of and amount of services provided. |
| **Activities** | **Responsibility** | **Timeline** | **Final Approval** | **Partners** | **Potential Barriers**  |
| Support LCSW to visit local meetings (e.g. community center, LEPC) to increase presence and visibility in the community. | Practice Administrator | 6 months | CEO | LEPC and Community Center | Time |
| Work to determine LCSW’s role in organizing, facilitating, and maintaining local support groups. | P.A. | 1 year | CEO | Providers | Time, volunteers |
| Determine feasibility of starting Grandparents Raising Grandchildren support group. | LCSW | 1 year | CEO | Providers | Time |
| Explore feasibility of cooperating with local churches to enable and sustain support groups for the community (e.g. grief support).  | LCSW/CEO | 2 years | CEO | Churches/CEO | Time |
| **Needs Being Addressed by this Strategy:*** 1. The majority of respondents (50.8%) rated their community as “Somewhat healthy.”
* 2. Top health concerns for the community were “Alcohol/substance use” (59.4%), “Mental health issues (depression, anxiety, PTSD, etc.)” (36.7%), and “Overweight/obesity” (25.0%).
* 3. The second top component of a healthy community was “Access to healthcare services” (34.1%).
* 4. Most respondents had a “Good” (45.7%) or “Fair” (34.6%) knowledge of RMH services; the top methods of learning about available services were “Word of mouth/reputation” (61.7%), “Friends/family” (50.8%), “Healthcare provider” (32.8%), and “Social media/Facebook” (25.0%).
* 5. Access to healthcare would be improved with “More primary care providers (MD/DO)” (45.6%), “More information about available services” (36.8%), and “More Nurse Practitioners/Physician Assistants” (28.0%).
* 6. 50.0% of respondents felt lonely or isolated 1-2 days per month or more.
* 7. 58.7% of respondents experienced “Moderate” or “High” stress.
* 8. 19.0% of respondents rated their mental health as “Fair” and 3.2% rated theirs as “Poor.”
* 9. 46.0% of respondents indicated their lives have been impacted by substance use.
* 10. Key informants identified mental health and alcohol/drug use as top concerns in the community.
* 11. Key informants expressed the desire for more support groups in the community.
 |
| **Anticipated Impact(s) of these Activities:*** Improved awareness and utilization of services and programs
* Strengthened collaboration between RMH and local LCSW
* Build community capacity
* Increase access to healthcare services
* Increased community knowledge of services and resources
* Improved health outcomes
 |
| **Plan to Evaluate Anticipated Impact(s) of these Activities:*** Track RMH support of LCSW
* Track LCSW visits to local meetings and groups
* Track efforts made to create and facilitate support groups
* Track progress made on Grandparents Raising Grandchildren support group
* Track cooperation with local churches
 |
| **Measure of Success:** RMH will have supported the local LCSW to start 2 support groups by the 2027 CHNA. |

|  |
| --- |
| **Goal 1:** **Improve access to mental and behavioral health resources in Musselshell County.** |
| **Strategy 1.2:** Continue to support other mental and behavioral health resources in the community.  |
| **Activities** | **Responsibility** | **Timeline** | **Final Approval** | **Partners** | **Potential Barriers**  |
| Continue to coordinate with and support local school counselors and LCSWs.  | Assistant Medical Director/PA | 1 year | CEO | Local schools | Access to schools |
| Continue to explore ways to bolster in-patient mental health resources.  | Assistant Medical Director/PA and Director of Nursing | Ongoing | CEO | Outside resources | Lack of mental health providers and resources |
| **Needs Being Addressed by this Strategy:*** 1. The majority of respondents (50.8%) rated their community as “Somewhat healthy.”
* 2. Top health concerns for the community were “Alcohol/substance use” (59.4%), “Mental health issues (depression, anxiety, PTSD, etc.)” (36.7%), and “Overweight/obesity” (25.0%).
* 3. The second top component of a healthy community was “Access to healthcare services” (34.1%).
* 4. Most respondents had a “Good” (45.7%) or “Fair” (34.6%) knowledge of RMH services; the top methods of learning about available services were “Word of mouth/reputation” (61.7%), “Friends/family” (50.8%), “Healthcare provider” (32.8%), and “Social media/Facebook” (25.0%).
* 5. Access to healthcare would be improved with “More primary care providers (MD/DO)” (45.6%), “More information about available services” (36.8%), and “More Nurse Practitioners/Physician Assistants” (28.0%).
* 6. 50.0% of respondents felt lonely or isolated 1-2 days per month or more.
* 7. 58.7% of respondents experienced “Moderate” or “High” stress.
* 8. 19.0% of respondents rated their mental health as “Fair” and 3.2% rated theirs as “Poor.”
* 9. 46.0% of respondents indicated their lives have been impacted by substance use.
* 10. Key informants identified mental health and alcohol/drug use as top concerns in the community.
 |
| **Anticipated Impact(s) of these Activities:*** Improved awareness and utilization of services and programs
* Strengthened collaboration between community partners
* Build community capacity
* Increase access to healthcare services
* Increased community knowledge of services and resources
* Improved health outcomes
* Service, policy, and resources development
* Improve access to high quality, coordinated care
* Strengthen community partnerships
 |
| **Plan to Evaluate Anticipated Impact(s) of these Activities:*** Track support of LCSW
* Track support of local school counselors
* Evaluate potential new in-patient mental health resources as they are learned of
 |
| **Measure of Success:** Host mental health meeting in collaboration with school leaders to determine feasibility of ongoing partnership.  |

|  |
| --- |
| **Goal 2:** **Enhance community awareness of health resources and services offered through RMH.** |
| **Strategy 2.1:** Enhance marketing and publicity efforts to increase visibility of RMH in the community.  |
| **Activities** | **Responsibility** | **Timeline** | **Final Approval** | **Partners** | **Potential Barriers**  |
| Inquire about putting hospital advertising materials in new kiosk downtown.  | HR/Marketing Director | 6 months | CEO/RCP | RCP | Space |
| Explore re-starting RMH presence on local radio station.  | CEO | Ongoing | CEO | Roundup Radio Station | Availability |
| Continue to engage with LEPC meetings and utilize this forum to advertise RMH services and resources.  | Assistant Medical Director/PA | Ongoing | N/A | LECP | Availability |
| Continue to attend community events (e.g. Market on Main, Community Job Fair) to increase hospital presence in the community.  | Assistant Medical Director/PA , HR/Marketing Director, and Trauma Coordinator | Ongoing | CEO | Market on Main and Chamber | Availability and resources |
| **Needs Being Addressed by this Strategy:*** 3. The second top component of a healthy community was “Access to healthcare services” (34.1%).
* 4. Most respondents had a “Good” (45.7%) or “Fair” (34.6%) knowledge of RMH services; the top methods of learning about available services were “Word of mouth/reputation” (61.7%), “Friends/family” (50.8%), “Healthcare provider” (32.8%), and “Social media/Facebook” (25.0%).
* 5. Access to healthcare would be improved with “More primary care providers (MD/DO)” (45.6%), “More information about available services” (36.8%), and “More Nurse Practitioners/Physician Assistants” (28.0%).
* 12. 93.0% of respondents have seen a primary care provider in the last three years, and 26.9% saw that provider at Billings Clinic.
* 13. Key informants identified the need for more communication about currently offered programs and services.
 |
| **Anticipated Impact(s) of these Activities:*** Improved awareness and utilization of RMH in the community
* Strengthened collaboration between community partners
* Increase access to healthcare services
* Increased community knowledge of services
* Improved health outcomes
* Service, policy, and resources development
 |
| **Plan to Evaluate Anticipated Impact(s) of these Activities:*** Track efforts to put RMH materials in downtown kiosk
* Track communication and coordination with local radio station
* Track RMH use of LEPC meetings to advertise resources and services
* Track community partners reached through LEPC meetings
* Track community events attended
* Track reach from community events
 |
| **Measure of Success:** Overall volume increase in use of outpatient services.  |

|  |
| --- |
| **Goal 2:** **Enhance community awareness of health resources and services offered through RMH.** |
| **Strategy 2.2:** Reinvigorate partnerships and relationships with various community entities. |
| **Activities** | **Responsibility** | **Timeline** | **Final Approval** | **Partners** | **Potential Barriers**  |
| Continue community education efforts.  | SLT | Ongoing | SLT | Radio, School System, Chamber, Churches, Senior Center | Time and availability |
| Define the role of the Hospital Foundation and its relationship with RMH. | CEO | Ongoing | Board | Foundation coordinator and members | Participation |
| Continue to support and collaborate with the Hospital Foundation. | Foundation Coordinator | Ongoing | CEO | Foundation Board | Infrequency of events |
| Explore methods of increasing awareness of CHW presence and services through the clinic.  | Practice Administrator | Ongoing | Practice Administrator | MHN, CHW, Visiting Nurse Service | Internal referrals awareness, increasing education of services for CHW |
| **Needs Being Addressed by this Strategy:*** 3. The second top component of a healthy community was “Access to healthcare services” (34.1%).
* 4. Most respondents had a “Good” (45.7%) or “Fair” (34.6%) knowledge of RMH services; the top methods of learning about available services were “Word of mouth/reputation” (61.7%), “Friends/family” (50.8%), “Healthcare provider” (32.8%), and “Social media/Facebook” (25.0%).
* 5. Access to healthcare would be improved with “More primary care providers (MD/DO)” (45.6%), “More information about available services” (36.8%), and “More Nurse Practitioners/Physician Assistants” (28.0%).
* 12. 93.0% of respondents have seen a primary care provider in the last three years, and 26.9% saw that provider at Billings Clinic.
* 13. Key informants identified the need for more communication about currently offered programs and services.
* 14. Key informants expressed the desire for more transportation options in Roundup.
 |
| **Anticipated Impact(s) of these Activities:*** Improved awareness and utilization of services and programs
* Strengthened collaboration between community partners
* Build community capacity
* Increase access to healthcare services
* Increased community knowledge of services
* Improved health outcomes
* Service, policy, and resources development
 |
| **Plan to Evaluate Anticipated Impact(s) of these Activities:*** Track community education events and sponsorships
* Track participation at community education events
* Create document outlining relationship between Hospital Foundation and RMH
* Track support of Hospital Foundation
* Evaluate best methods of increasing awareness of CHW in the clinic
 |
| **Measure of Success:** Foundation dollars raised. |

|  |
| --- |
| **Goal 3:** **Bolster access to specialty care services available through Roundup Memorial Healthcare.** |
| **Strategy 3.1:** Explore introduction of new specialty services offered through RMH. |
| **Activities** | **Responsibility** | **Timeline** | **Final Approval** | **Partners** | **Potential Barriers**  |
| Explore re-introducing podiatry visiting specialists.  | Practice Administrator | 1 year | CEO | Podiatry office | Volumes, distance to Billings |
| Explore feasibility of bringing visiting dermatology specialty services to RMH. | Practice Administrator | 1 year | CEO | Dermatology office | Patient volumes, doctor availability |
| Determine if patient load is sufficient to warrant an ortho PA at RMH.  | Practice Administrator | 2 years | CEO | Ortho office | Volumes, availability, and distance |
| **Needs Being Addressed by this Strategy:*** 3. The second top component of a healthy community was “Access to healthcare services” (34.1%).
* 5. Access to healthcare would be improved with “More primary care providers (MD/DO)” (45.6%), “More information about available services” (36.8%), and “More Nurse Practitioners/Physician Assistants” (28.0%).
* 15. Respondents expressed the desire for “Dermatology” services (34.3%) and “Orthopedic services” (17.6%).
* 16. 10.7% of respondents utilized a “Hearing check” as preventative service.
* 17. 33.3% of respondents said they delayed or deferred receiving care, and the top reasons were “Qualified provider not available” (34.1%) and “Too long to wait for appointment” (26.8%).
 |
| **Anticipated Impact(s) of these Activities:*** Increase access to specialty care services
* Increase access to high quality, coordinated healthcare services
* Improved health outcomes
* Service, policy, and resources development
* Enhanced patient care and follow-up capabilities
 |
| **Plan to Evaluate Anticipated Impact(s) of these Activities:*** Track progress concerning podiatry re-introduction
* Evaluate demand for visiting dermatology services
* Evaluate patient load for potential ortho PA
 |
| **Measure of Success:** Bring in at least one additional service line to the clinic.  |

# Needs Not Addressed and Justification

|  |  |
| --- | --- |
| **Identified health needs unable to address****by Roundup Memorial Healthcare** | **Rationale** |
| 1. A top health concern was “Overweight/obesity” (25.0%), and the top three educational programs respondents expressed interest in were “Fitness” (39.8%), “Weight loss” (31.5%), and “Health and wellness” (30.6%). 31.8% of respondents got physical activity 3-5 times per month or less.
 | Other goals presented were higher priority for the hospital to address. We are unable to offer services at this time surrounding overweight/obesity. Tried walk with ease historically and only staff attended. |
| 1. The third top component of a healthy community was “Affordable housing” (29.5%), and 54.8% of respondents did not think that there was adequate and affordable housing available in the community.
 | Housing is outside of the hospital scope of service.  |

# Dissemination of Needs Assessment

Roundup Memorial Healthcare, “RMH,” disseminated the community health needs assessment and implementation plan by posting both documents conspicuously on their website (<https://www.rmhmt.org/documents/RMH_2024_CHNAReport_FinalRB-edits.pdf>). as well as having copies available at the facility should community members request to view the community health needs assessment or the implementation planning documents.

The Steering Committee, which was formed specifically as a result of the CHSD (Community Health Services Development) process to introduce the community to the assessment process, will be informed of the implementation plan to see the value of their input and time in the CHSD process as well as how RMH is utilizing their input. The Steering Committee, as well as the Board of Directors, will be encouraged to act as advocates in Musselshell County as the facility seeks to address the healthcare needs of their community.

Furthermore, the board members of RMH will be directed to the hospital’s website to view the complete assessment results and the implementation plan. RMH board members approved and adopted the plan on **September 5, 2024**. Board members are encouraged to familiarize themselves with the needs assessment report and implementation plan, so they can publicly promote the facility’s plan to influence the community in a beneficial manner.

Written comments on this 2024-2027 Roundup Memorial Healthcare Community Benefit Strategic Plan can be submitted to:

*Attn: Administration*

Roundup Memorial Healthcare

1202 3rd St. W

PO Box 40

Roundup, MT 59072

Please reach out to Roundup Memorial Healthcare’s HR & Marketing Director, Rachel Brewer, at 406-323-4938 or Rbrewer2@rmhmt.org with questions.